## Example
WSFN - PROJECT COST VARIATION SHEET
Local Government: |  | Black Stump |  |  |  |  | Date: |  | 2032-08-23
Road Name: |  | Black stump to Timbuktu |  |  |  |  | Financial Year: |  | 32/33 | Note - this was the section to be completed in the 31/32 Yr, now to be completed in the current 32/33 Yr.
| SLK From: | 0 | SLK To: |  | 23 | Total Project Length (km): |  |  | 23
Note : All Costs are Ex GST |  |  | Previous Budget Revision No. |  | 0 | Revised Budget Variation No. |  | 1
|  |  | Previous Budget Date |  | 2031-10-22 | Revised Budget Date |  | 2032-08-23 | Total Cost Variation | Reason for Variation
Item No. | Item Description | Unit | Original Qty | Original Cost Rate | Original Cost | Revised Qty | Revised Cost Rate | Revised Cost
1 | Average Normal Hourly Labour Cost Rates with PWO across the crew | Hrs | 2856 | 60.25 | 172074 | 2856 | 63.262 | 180676.272 | 8602.272 | The Black Stump Shire have raised average Labour Cost Rates by 5% across the board from the 31/32 Yr to the 32/33 Yr. See the attached highlighted cost sheets.
2 | Average 1.5 x Overtime Hourly Labour Cost Rates with PWO across the crew | Hrs | 305 | 90.375 | 27564.375 | 305 | 94.9058 | 28946.269 | 1381.894 | The Black Stump shire have raised average Labour Cost Rates by 5% across the board from the 31/32 Yr to the 32/33 Yr.
3 | Plant Costs | Hrs | Various | Various | 134081 | Various | Various | 153271 | 19190 | See the attached highlighted cost sheets showing the Plant Hrs have not altered, apart from a Water Tanker Truck being added with Hrs and this has reduced the required Hrs on the smaller Water Truck CN2. Generally, the POC rates have been increased due mainly to the extraordinary diesel cost increases around Feb 2032.
4
5
6
7 |  |  |  |  | Some cells and columns have formulas, highlighted yellow, NB these are not protected if you overwrite the formulas will be gone.
8
9
10
11
12
13
14 | If more rows are needed insert more
15
16
|  |  |  | Variance between new Budget Cost & Previous Budget Cost |  |  |  |  | 29174.166
|  |  | Original Budget Cost - Rev : |  |  | 0 | at date: | 2031-10-22 | 1111328 | This value included a 5% contingency allowance ONLY.
|  |  | Revised Budget Cost - Rev : |  |  | 1 | at date: | 2032-08-23 | 1355429 | This value includes a 10% contingency allowance.
244101
GENERAL NOTES
1 | DESPITE THE GEOTECHNICAL TESTING BEING CARRIED OUT ON THE SECTION FROM SLK 0.1 - 10.44 IN MARCH 2031, THE PAVEMENT DESIGN FOR THE SECTION FROM SLK 7.13 - 10.44 WAS NOT AVAILABLE WHEN THE REQUEST STATED IN NOTE 1 ABOVE WAS PROPOSED. SUBSEQUENTLY, THE PROPOSED TREATMENTS AND SUBSEQUENT COSTINGS WERE ESTIMATES ONLY, IN THE OCTOBER 2031 COSTINGS. THE FINAL PAVEMENT DESIGN FOR THIS 3.13KM SECTION WAS NOT COMPLETE UNTIL 19 DECEMBER 2031 (FOLLOWING ADDITIONAL GEOTECHNICAL INVESTIGATION WORK CONDUCTED IN OCTOBER 2031), AND IT REVEALED SIGNIFICANTLY GREATER REQUIRED PAVEMENT RECONSTRUCTION TREATMENTS (AND SUBSEQUENT COSTS) THAN WAS ESTIMATED IN OCTOBER 2031.
2
3
4
5
6
7 | WSFN would like to Thank RMECS for the original spreadsheet.
WSFN VS
Note on O9: Peter Hall: This is mainly an overview of the reason and cannot be the only evidence. Supporting documents are provided then the chance of a successful variation improves.
Example

## Variation
WSFN - PROJECT COST VARIATION SHEET
Local Government: | [6 empty] | Date:
Road Name: | [6 empty] | Financial Year:
| SLK From: |  | SLK To: |  |  | Total Project Length (km): |  |  | 0
Note : All Costs are Ex GST |  |  | Previous Budget Revision No. |  | 0 | Revised Budget Variation No. |  | 1
|  |  | Previous Budget Date |  |  | Revised Budget Date |  |  | Total Cost Variation | Reason for Variation
Item No. | Item Description | Unit | Original Qty | Original Cost Rate | Original Cost | Revised Qty | Revised Cost Rate | Revised Cost
1 |  |  |  |  | 0 |  |  | 0 | 0
2 |  |  |  |  | 0 |  |  | 0 | 0
3 |  |  |  |  | 0 |  |  | 0 | 0
4 |  |  |  |  | 0 |  |  | 0 | 0
5 |  |  |  |  | 0 |  |  | 0 | 0
6 |  |  |  |  | 0 |  |  | 0 | 0
7 |  |  |  |  | 0 |  |  | 0 | 0
8 |  |  |  |  | 0 |  |  | 0 | 0
9 |  |  |  |  | 0 |  |  | 0 | 0
10 |  |  |  |  | 0 |  |  | 0 | 0
11 |  |  |  |  | 0 |  |  | 0 | 0
12 |  |  |  |  | 0 |  |  | 0 | 0
13 |  |  |  |  | 0 |  |  | 0 | 0
14 |  |  |  |  | 0 |  |  | 0 | 0
15 |  |  |  |  | 0 |  |  | 0 | 0
16 |  |  |  |  | 0 |  |  | 0 | 0
17 |  |  |  |  | 0 |  |  | 0 | 0
18 |  |  |  |  | 0 |  |  | 0 | 0
19 |  |  |  |  | 0 |  |  | 0 | 0
20 |  |  |  |  | 0 |  |  | 0 | 0
|  |  |  | Variance between new Budget Cost & Previous Budget Cost |  |  |  |  | 0
|  |  | Original Budget Cost - Rev : |  |  |  | at date: | 0
|  |  | Revised Budget Cost - Rev : |  |  |  | at date: | 0
0
GENERAL NOTES
1
2
3
4
5
6