## Construction Projects
WHEATBELT SECONDARY FREIGHT NETWORK - PROGRAM REPORTS
YEAR ________ (1 July 20___ to 30 June 20___)
LOCAL GOVERNMENT | ROAD NAME | START SLK KMS | END SLK KMS | LENGTH KMS | PROJECT PHASE (CONSTRUCTION OR DEVELOPMENT) | PROJECT SCOPE OF WORKS (DESCRIPTION OF WORKS) | ROUTE NAME/ NUMBER | PROJECT YEAR (BUDGET $) | ESTIMATED COST TO COMPLETE ($) | START DATE (ESTIMATED) | COMPLETION DATE (ESTIMATED) | % COMPLETE | PROJECT STATUS REPORT AS AT ________________________
0
PLEASE FILL OUT THE COLUMNS HIGHLIGHTED IN YELLOW
LG - Year 5 | ROAD NAME | START SLK | END SLK | LENGTH KMS | PROJECT PHASE | PROJECT SCOPE OF WORKS | ROUTE | YEAR 6 - 24/25 |  | START DATE | EST COMPLETION | % COMPLETE | PROJECT STATUS REPORT AS AT 15 AUGUST 2024
Cuballing | Cuballing East 4050006 | 0.10 10.48 | 2.42 12.80 | 4.64 | Construction | Reconstruction / Upgrade Works to achieve a minimum 10.0m carriageway and 8.0m seal width and deeper stronger pavement on section from SLK 0.10 - 2.42 & 10.48 - 12.80 totalling 4.64 km. Upgrade works includes lime stabilisation of 11,400 m2 of subgrade of sections . Includes extending 5 of 9 existing Culverts and installing new P/Cast End Treatments to 8 culverts and Cast Insitu End Treatments to 1 culvert (2 reqd), installing 1 x new culvert across carriageway opposite Parsons Rd Intersection, and installing 6 x new crossover culverts. Upgrade the Bullara St, Munro St, Parsons Rd & Pauley Rd T-Junction intersections at SLK 0.47, 0.99, 1.86 and 10.85 respectively by widening out and resurfacing with Chip Seal. | Cuballing to Wickepin Route 37 | 1415738 |  | 2023-10-02
Cuballing | Cuballing East 4050006 | 2.42 | 7.13 | 4.71 | Construction | Apply final seal to reconstruction works completed 2022/23 Yr | Cuballing to Wickepin Route 37 | 235235 |  | 2024-03-01
Fill this out when an issue is discovered that was not anticipated
|  |  | Location of Issue |  |  |  | PROGRAM CONTINGENCY NOTIFICATION
|  | Project Identification | Start | Finish | Length | Description of issue and proposed remedy |  | Estimated value |  |  | Final Value |  | Comments
| Example Only | Culvert | 2.3 | 2.7 | 0.4 | Subsoil water enccountered, will need to build intersection drain to divert the flow |  | 25000 |  |  | 19280 |  | Water is constantly flowing out of the diversion when completed
After completing this form, please email to: |  |  | executiveofficer@wsfn.wa.gov.au
Note on I10: Peter Hall: Total budget $1,888,752 Variation approved SC June 2024 meeting $282,487 Total new budget $2,171,239
Note on I11: Racelis Revised project cost - SC on 28 June 2024

## DEVELOPMENT PROJECTS
THIS REPORT IS FOR THE PREVIOUS MONTH 1ST TO END OF MONTH
ONLY NEED TO FILL IN THE YELLOW CELLS - OVERWRITE LAST MONTHS INFORMATION
LOCAL GOVERNMENT | ROAD NAME | START SLK KMS | END SLK KMS | LENGTH KMS | PROJECT PHASE (CONSTRUCTION OR DEVELOPMENT) | PROJECT SCOPE OF WORKS (DESCRIPTION OF WORKS) | ROUTE NAME/ NUMBER | PROJECT YEAR (BUDGET $) | ESTIMATED COST TO COMPLETE ($) | START DATE (ESTIMATED) | COMPLETION DATE (ESTIMATED) | % COMPLETE | PROJECT STATUS REPORT AS AT ________________________
Fill this out when an issue is discovered that was not anticipated
|  |  | Location of Issue |  |  |  | PROGRAM CONTINGENCY NOTIFICATION
|  | Project Identification | Start | Finish | Length | Description of issue and proposed remedy |  | Estimated value |  |  | Final Value |  | Comments
| Example | Culvert | 2.3 | 2.7 | 0.4 | Subsoil water enccountered, will need to build intersection drain to divert the flow |  | 25000 |  |  | 19280 |  | Water is constantly flowing out of the diversion when completed

## IPP
WHEATBELT SECONDARY FREIGHT NETWORK - PROGRAM REPORTS
YEAR ________ (1 July 20___ to 30 June 20___)
INDIGENOUS PARTICIPATION PROGRAM (IPP)
[9 empty] | CONTRACTOR INFORMATION |  |  |  | SHIRE INFORMATION |  |  |  | DO NOT DELETE FORMULAS |  |  |  | PROJECT CASH FLOW
Local Government | Route Number | Road Name | START SLK | END SLK | LENGTHS KMS | Development/Construction | Project Start Date | Project Completion Date (or ECD) | Last Month number of project staff Contractor Total | Last Month number of hours worked Contractor Total | Last Month number of project staff Contractor Aboriginal | Last Month number of hours worked Contractor Abooriginal | Last Month number of project staff LG Total | Last Month number of project hours worked LG Total | Last Month Number of staff - Project Total (Contractor + LG) | Last Month Number of hours worked - Project Total (Contractor + LG) | Number of Staff Project Total (Contractor + LG) | Number of hours Worked Project Total (Contractor + LG) | Number of Aboriginal staff - Project Total (Contractor + LG) | Number of hours worked Aboriginal - Project Total (Contractor + LG) | Last Month Total $ Spent Project | Last Month $ Spent All Suppliers | Last Month $ Spent Aboriginal Suppliers | Types of roles undertaken by Aboriginal Staff (List)
[17 empty] | 0 | 0 | 0 | 0
[17 empty] | 0 | 0 | 0 | 0
[17 empty] | 0 | 0 | 0 | 0